## Sheet1
Sequence | Environment | Type | Tools | Activity Type | Start Date | End Date | Priority | Resource | Status | Issue | Remark
1 | QA | Foundation | ElasticSearch | Document Configuration | 2017-11-03 | 2017-11-03 | High | Anand | Almost complete - 11/06
2 | QA | Foundation | ElasticSearch | Terraform Script Template | 2017-11-03 | 2017-11-06 | High | Anand | On Hold | Matt to increase Elastic Load Balancer limit | Matt has opened AWS service request to increase ELB limit
3 | QA | Foundation | Kibana X-Pack | Document Configuration | 2017-11-03 | 2017-11-03 | Talk to Ken | Arvind | On Hod |  | We are planning to decommission x-pack
4 | QA | Foundation | Kibana X-Pack | Terraform Script Template | 2017-11-03 | 2017-11-06 | Talk to Ken | Ananth | On Hold | License for Kibana X-Pack Security is expired. Enterprise License needs to be ordered by NYL | We are planning to decommission x-pack
5 | QA | Foundation | Kafka/Mirrormaker | Document Configuration | 2017-11-03 | 2017-11-03 |  | Shiva | WIP - 11/07
6 | QA | Foundation | Kafka/Mirrormaker | Terraform Script Template | 2017-11-06 | 2017-11-07 |  | Nandakumar | Not Started - 11/08
7 | QA | Foundation | Zookeeper | Document Configuration | 2017-11-06 | 2017-11-06 |  | Shiva | WIP - 11/07
8 | QA | Foundation | Zookeeper | Terraform Script Template | 2017-11-07 | 2017-11-08 |  | Nandakumar | Not Started - 11/09
9 | QA | Foundation | Logstash | Document Configuration | 2017-11-03 | 2017-11-03 |  | Arvind | Completed
10 | QA | Foundation | Logstash | Terraform Script Template | 2017-11-03 | 2017-11-06 |  | Ananth | Not Started - 11/08
11 | QA | Foundation | KDC Master | Document Configuration | 2017-11-07 | 2017-11-07 |  | Shiva | WIP - 11/07 | Copying Key Tabs from KDC Master to Kafka Zookeeper
12 | QA | Foundation | KDC Master | Terraform Script Template | 2017-11-08 | 2017-11-08 |  | Srilakshmi | Not Started - 11/08
13 | QA | Foundation | KDC slave | Document Configuration | 2017-11-08 | 2017-11-08 |  | Shiva | Not Started - 11/08
14 | QA | Foundation | KDC slave | Terraform Script Template | 2017-11-07 | 2017-11-08 |  | Arvind | Not Started - 11/08
15 | QA | Foundation | Consul | Document Configuration | 2017-11-03 | 2017-11-03 |  | Arun | WIP
16 | QA | Foundation | Consul | Terraform Script Template | 2017-11-06 | 2017-11-07 |  | Anand | On Track
17 | QA | Foundation | Drools Workbench | Document Configuration | 2017-11-03 | 2017-11-03 |  | Varuna | Not Started - 11/08
18 | QA | Foundation | Drools Workbench | Terraform Script Template | 2017-11-08 | 2017-11-09 |  | Nandakumar | Not Started - 11/09
19 | QA | Foundation | Dynamo DB | Document Configuration | 2017-11-03 | 2017-11-03 |  | Shyam | WIP - 11/07
20 | QA | Foundation | Dynamo DB | Terraform Script Template | 2017-11-06 | 2017-11-06 |  | Srilakshmi | Not Started - 11/08
21 | QA | Microservice | Calculator | Document Configuration | 2017-11-06 | 2017-11-06 |  | Shyam | WIP - 11/07
22 | QA | Microservice | Calculator | Terraform Script Template | 2017-11-07 | 2017-11-07 |  | Srilakshmi | Not Started - 11/09
23 | QA | Microservice | OPP Calculator | Document Configuration | 2017-11-07 | 2017-11-07 |  | Shyam | WIP - 11/07
24 | QA | Microservice | OPP Calculator | Terraform Script Template | 2017-11-08 | 2017-11-08 |  | Ananth | Not Started - 11/08
25 | QA | Microservice | Elastic Cache | Document Configuration | 2017-11-03 | 2017-11-03 |  | Ananth | WIP - 11/07
26 | QA | Microservice | Elastic Cache | Terraform Script Template | 2017-11-06 | 2017-11-06 |  | Ananth | Not Started - 11/09
27 | Staging | Foundation | ElasticSearch | Terraform Script Template |  |  |  | Anand
28 | Staging | Foundation | Kibana & X-Pack | Terraform Script Template |  |  |  | Ananth
29 | Staging | Foundation | Kafka/Mirrormaker | Terraform Script Template |  |  |  | Nandakumar
30 | Staging | Foundation | Zookeeper | Terraform Script Template |  |  |  | Nandakumar
31 | Staging | Foundation | Logstash | Terraform Script Template |  |  |  | Ananth
32 | Staging | Foundation | KDC Master | Terraform Script Template |  |  |  | Srilakshmi
33 | Staging | Foundation | KDC slave | Terraform Script Template |  |  |  | Arvind
34 | Staging | Foundation | Consul | Terraform Script Template |  |  |  | Anand
35 | Staging | Foundation | Drools Workbench | Terraform Script Template |  |  |  | Nandakumar
36 | Staging | Foundation | Dynamo DB | Terraform Script Template |  |  |  | Srilakshmi
37 | Staging | Microservice | Calculator | Terraform Script Template |  |  |  | Srilakshmi
38 | Staging | Microservice | OPP Calculator | Terraform Script Template |  |  |  | Ananth
39 | Staging | Microservice | Elastic Cache | Terraform Script Template |  |  |  | Ananth
40 | Dev Integration | Foundation | ElasticSearch | Terraform Script Template |  |  |  | Anand
41 | Dev Integration | Foundation | Kibana & X-Pack | Terraform Script Template |  |  |  | Ananth
42 | Dev Integration | Foundation | Kafka/Mirrormaker | Terraform Script Template |  |  |  | Nandakumar
43 | Dev Integration | Foundation | Zookeeper | Terraform Script Template |  |  |  | Nandakumar
44 | Dev Integration | Foundation | Logstash | Terraform Script Template |  |  |  | Ananth
45 | Dev Integration | Foundation | KDC Master | Terraform Script Template |  |  |  | Srilakshmi
46 | Dev Integration | Foundation | KDC slave | Terraform Script Template |  |  |  | Arvind
47 | Dev Integration | Foundation | Consul | Terraform Script Template |  |  |  | Anand
48 | Dev Integration | Foundation | Drools Workbench | Terraform Script Template |  |  |  | Nandakumar
49 | Dev Integration | Foundation | Dynamo DB | Terraform Script Template |  |  |  | Srilakshmi
50 | Dev Integration | Microservice | Calculator | Terraform Script Template |  |  |  | Srilakshmi
51 | Dev Integration | Microservice | OPP Calculator | Terraform Script Template |  |  |  | Ananth
52 | Dev Integration | Microservice | Elastic Cache | Terraform Script Template |  |  |  | Ananth